## Sheet1
Story | Sps | Sprint | SP | hours
Set up python flask service | 1 | 1 | 1 | 1
set up Angular app | 1 | 1 | 3 | 4
Design login page | 1 | 1 | 5 | 8
Develop token based security | 3 | 1
Pagination and grid functionalities front end | 3 | 1 | Sprint Frequency | 8 hours
Pagination and grid functionalities back end | 3 | 2
Design modal service | 1 | 2
Backend end points for create CR | 1 | 2
Front end implementation for create CR | 1 | 2
Backend end points for update CR | 1 | 2
Front end implementation for update CR | 1 | 2
Implement guard protection and session management | 1 | 3
UI responsiveness | 1 | 3
Bug fixes | 3 | 3
Unit test cases for change request page | 3 | 3